LENDING READINESS PARTNERS

Partner Outreach Playbook

A repeatable 12-week lender and Realtor recruitment system

Helping More Borrowers Become Lending Ready.

# Weekly Activity Targets

| Activity | Minimum | Target | Tracked In |
| --- | --- | --- | --- |
| New qualified contacts | 25 | 50 | CRM |
| Personalized emails | 20 | 40 | CRM |
| Phone calls | 10 | 25 | Call log |
| LinkedIn connections | 15 | 30 | LinkedIn/CRM |
| Partner meetings | 2 | 5 | Calendar |
| Referral follow-ups | All | All within 1 business day | CRM |

# 12-Week Sequence

## Week 1: Foundation

Finalize collateral, secure referral form, CRM stages, scheduling link, and partner FAQ.

## Week 2: Warm Network

Contact existing business relationships, Realtors, insurance agents, builders, and community partners.

## Week 3: Loan Officer Prospecting

Build a local list and begin the 12-email sequence with personalized introductions.

## Week 4: Educational Value

Publish a borrower-readiness checklist and invite partners to a short lunch-and-learn.

## Week 5: Office Visits

Deliver folders or digital kits to selected brokerages and branch offices.

## Week 6: Realtor Expansion

Launch the Realtor-specific sequence and co-branded buyer-readiness offer.

## Week 7: Follow-Up

Call engaged contacts, answer objections, and schedule implementation meetings.

## Week 8: Partner Onboarding

Complete partner profile, communication consent workflow, referral test, and co-brand setup.

## Week 9: Community Visibility

Present a homebuyer-readiness workshop with a lender or Realtor partner.

## Week 10: Proof and Process

Share anonymized process examples without promising outcomes or revealing client information.

## Week 11: Pipeline Review

Review lead sources, meetings, referrals, conversion rates, and stalled opportunities.

## Week 12: Optimize and Repeat

Improve messaging, retire weak channels, double down on productive partner segments, and begin the next cycle.

# CRM Stages

Prospect identified

Initial outreach sent

Engaged

Meeting scheduled

Partner qualified

Agreement/process review

Onboarding

Active referral partner

Dormant/reactivation

Not a fit

# Partner Qualification Questions

How often do applicants need additional credit preparation?

What happens to applicants who are not currently approvable?

What information may be shared with a referral partner, and what written consent is required?

Who owns follow-up with the borrower?

What turnaround and update cadence is useful?

Does the company require vendor approval, compliance review, insurance, or a written agreement?

Which marketing claims and co-branding rules apply to the lender’s organization?